## Sheet1
Sr. no. | Phase | Task | Owner | Proposed Start date | Proposed End date | Actual Start date | Actual End Date | Status
1 | Project Initiation | Define project scope and objectives. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13 | Completed
|  | Identify stakeholders and their requirements. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13 | Completed
|  | Set up project team roles and responsibilities. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13 | Completed
|  | Conduct initial research on healthcare systems. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13 | Completed
2 | Planning and Design | Data modelling and schema design. | Riya Deshpande | 2023-10-14 | 2023-10-24 |  |  | Completed
|  | Create user stories and use cases for the application. | Mitali Juvekar |  |  |  |  | Completed
|  | Design the user interface and UI mockups. | Riya Danve |  |  |  |  | Completed
|  | Choose the technology stack and tools for development. | Riya Adsul |  |  |  |  | Completed
| Development |  |  | 2023-10-25 | 2023-11-20 |  |  | In progress