## Sheet1
Sr. no. | Phase | Task | Owner | Proposed Start date | Proposed End date | Actual Start date | Actual End Date | Status
1 | Project Initiation | Define project scope and objectives. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13 | Completed
|  | Identify stakeholders and their requirements. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13
|  | Set up project team roles and responsibilities. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13
|  | Conduct initial research on healthcare systems. | Team | 2023-10-03 | 2023-10-13 | 2023-10-03 | 2023-10-13
2 | Planning and Design | Data modelling and schema design. | Riya Deshpande | 2023-10-14 | 2023-10-24 | 2023-10-14 | 2023-10-24 | Completed
|  | Create user stories and use cases for the application. | Mitali Juvekar | 2023-10-14 | 2023-10-24 | 2023-10-14 | 2023-10-24
|  | Design the user interface and UI mockups. | Riya Danve | 2023-10-14 | 2023-10-24 | 2023-10-14 | 2023-10-24
|  | Choose the technology stack and tools for development. | Riya Adsul | 2023-10-14 | 2023-10-24 | 2023-10-14 | 2023-10-24
3 | Development | Work on user authentication and user management. | Riya Deshpande | 2023-10-25 | 2023-11-20 | 2023-10-25 |  | In progress
|  | Implement patient data management features. | Riya Danve | 2023-10-25 | 2023-11-20 | 2023-10-25
|  | Integrate data visualization and notifications/alerts | Mitali Juvekar | 2023-10-25 | 2023-11-20 | 2023-10-25
|  | Work on creating the interfaces and notifications/alerts | Riya Adsul | 2023-10-25 | 2023-11-20 | 2023-10-25
|  | Collaborate on core functionality development and discuss applicable testing methods | Team | 2023-10-27 | 2023-11-20 | 2023-10-29
4 | Testing and Quality Assurance | Conduct unit testing to ensure individual components work correctly. | Riya Deshpande & Riya Adsul | 2023-11-21 | 2023-12-23 |  |  | Not begun
|  | Perform integration testing to verify interactions between system modules. | Riya Danve & Mitali Juvekar | 2023-11-23 | 2023-12-28
|  | Collaborate on bug identification and resolution. | Team | 2023-11-28 | 2023-11-30
|  | Assist in user acceptance testing and bug tracking. | Team | 2023-11-21 | 2023-12-30
5 | Deployment, training and documentation | Prepare the system for production use. | Riya Deshpande | 2023-12-01 | 2023-12-02 |  |  | Not begun
|  | Deploy the Patient Tracker System in a controlled environment. | Riya Adsul | 2023-12-03 | 2023-12-04
|  | Organize user training sessions and and gather user feedback | Riya Danve | 2023-12-04 | 2023-12-06
|  | Assist in system deployment and user training. | Mitali Juvekar | 2023-12-01 | 2023-12-06
|  | Documentation | Team | 2023-12-01 | 2023-12-05